Preparation of combined test beam with US-DHCAL
        Roman Pöschl
        LAL Orsay
        Calice Ecal Meeting
        8/2/11

---
(Rough) schedule
Beam time: 6/4/11 – 3/5/11 at the MTPF at FNAL
Attendees of test beam from in2p3:
- Marc Anduze 30/3/11 – 7/4/11
- Patrick Cornebise 30/3/11 – 11/4/11
- R.P.: 30/3/11 – 18/4/11
- Daniel Jeans 17/4/11 – 5/5/11
- Mickael Frotin 1/5/11 – 5/5/11
Will set up possibility for remote shifts – Watch out for details
Costs:
- Travel, Rental car, detector transport ~10 kEuro -> in2p3
- Per diem ~10kEuro -> ANL

---
Detector recommissioning
D. Jeans – CALICE TB Meeting 19/1/11

---
D. Jeans – CALICE TB Meeting 19/1/11

---
DAQ – Tests and repair of CRC boards
List compiled by Erika, Paul and R.P.
SER001 - At CERN for WHCAL (FE0, FE7 not properly working)
SER003 - At FNAL for DHCAL ok
SER004 - Killed during repair
SER005 - At CERN for WHCAL (all FE ok)
SER006 - At CERN for WHCAL (all FE ok)
SER007 - At LAL for ECAL but doesn't boot reliably, can probably be recovered
SER008 - At LAL for ECAL but unusable
SER009 - At CERN for WHCAL (FE0, FE5 not properly working)
SER010 - At UCL for repair, boots in the mean time but r/o problems!?
SER011 - At CERN for WHCAL (all FE ok)
SER012 - At FNAL for DHCAL ok
SER013 - At CERN for WHCAL (FE0 not properly working)
SER014 - At LAL for ECAL ok
SER015 - At CERN for WHCAL (all FE ok)
SER016 - At LAL for ECAL FE ok, but temperature readout faulty -> usable
SER017 - At CERN for WHCAL (only FE4 working)
SER018 - At LAL for ECAL ok
Debugging of CRCs happens in close collaboration with Paul Dauncey

---
Discussion of CRC situation
- Situation is critical but managable
Scenario 1: Parallel running at FNAL and CERN
-> Need (at least) one more working CRC to read out entire Ecal (+Trigger)
Scenario 2: No parallel running at FNAL and CERN
Enough CRCs are available
Conclusion:
- Will continue to debug CRCs, board 7 and 10 may be recovered
  Have time until end of march as CRCs can be carried in suitcase
- Prepare to take at least one CRC from CERN
Master solution: Avoid parallel running if possible
CERN schedule?

---
Schedule towards test beam
- 14/2/11 – 15/2/11 “Full” system test including slabs and all available
        CRCs
- 25/2/11 Shipment to FNAL for arrival at about 20 days later
- ~20/3/11 Arrival of detector at FNAL
- 30/3/11 Travel of in2p3 crew to FNAL and set-up of detector
In between: - Repair of CRCs or fetch from CERN (during AIDA kick-off?)
        Continuing close contact with Paul (and Erika)
        - Porting of DAQ s/w to modern computer and operating system
        (SL5)

---
Thanks to: F. Wicek, M. Gaspard, B. Debennerot, M. Fernandez, S. Trochet,
        J.C. Vanel, M. Warren
for their help during the re-commissioning of the Ecal